## Friday
Time | Task | Who | Comments
17:30 | Doors Open, Registration Desk starts
People checked in and receive Lanyards
Start Drink Service
People start mingling and have a drink
Short (all organising teams) meeting to tackle any last minute concerns, issues, questions.
18:00 | Official Start
General Mix and Mingle with hosts making an effort to introduce people around to other people with common interests
Finger food service
19:00 | Local Launch
Opening speech
Sponsors
Health and safety
20:00 | Hacking starts
Teams can find themselves a suitable table
Volunteers assist anyone needing help to form a team
22:00 | Doors Close

## Saturday
Time | Task | Who | Comments
8:00 | Doors open
13:00 | Lunch
18:30 | Dinner
22:00 | Doors Close
SUNDAY 13 JULY
9:00 | Doors open
Info sessions
13:00 | LUNCH
15:30 | Spirit of Govhack winner to Richard
16:00 | Setup for National Call and Event Close
Test Video Connection Between Sites
Short (all organising teams) meeting to tackle any last minute concerns, issues, questions.
16:30 | Organisers give 1 hour notice to Competition End
Entries need to go in Hackerspace, or to file share at the event
17:30 | Competition Closes
Closing remarks (James)
Thanks to sponsors and others (James)
Drinks & finger food served
18:00 | National Close via YouTube Video
"Spirit of GovHack" awarded
Give process for coming weeks
Details about national and local awards ceremonies
18:15 | Finish of national Close
Watch videos from Sydney team entries & Mingle
19:30 | Cleanup
Any final local announcements,
Participants help clean up etc
? 8:00 PM | Doors Close

## Sunday
Time | Task | Who | Comments
9:00 | Doors open
13:00 | Lunch
16:00 | Quick standup
Short (all organising teams) meeting to tackle any last minute concerns, issues, questions.
16:30 | The end is nigh
Organisers give 1 hour notice to Competition End
17:30 | Competition Closes
Closing remarks
Thanks to sponsors and others
Drinks & finger food served
19:00 | Cleanup
19:30 | Doors Close

## Opening Address Sponsor Talks
Time | Name | Organisation | Will Present?
Y / N

## Info Session List
Time | Name | Organisation | Topic
19:00